## Hoja1
ID | Task | Status | Start Date | Due Date | Duration | Y | 2018 | [28 empty] | Open | 20 | 66.67%
[6 empty] | M | Jun |  | Jul |  |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Doing | 9 | 30%
[6 empty] | CW | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | Closed | 1 | 3.333%
3. | Digital Electronics | Doing | 2018-07-30 | 2018-12-09 | 132 | bar: Jul 31 to Dec 50
3.1 | Microcontroller Requirements | Doing | 2018-07-30 | 2018-08-19 | 20 | bar: Jul 31; Aug 33 to Aug 34
3.1.1 | Define inputs needed for signal acquisition | Doing | 2018-08-06 | 2018-08-19 | 13 | bar: Aug 33
3.1.2 | Define outputs needed for digital potentiometers | Open | 2018-08-06 | 2018-08-19 | 13 | bar: Aug 33 to Aug 34
3.1.3 | Decide on communication protocol - MCU & Mobile 12/08/2018: Bluetooth | Closed | 2018-07-30 | 2018-08-12 | 13 | bar: Jul 31; Aug 33
3.2 | Programming Signal Acquisition | Doing | 2018-08-06 | 2018-09-02 | 27 | bar: Sep 36 to Sep 39
3.2.1 | Program signal acquisition in MCU | Doing | 2018-09-06 | 2018-09-12 | 6 | bar: Sep 36
3.2.2 | Design and implement signal validation tool | Open | 2018-08-06 | 2018-08-19 | 13 | bar: Sep 36 to Sep 37
3.2.3 | Test signal acquisition by using standard signals | Open | 2018-08-13 | 2018-08-19 | 6 | bar: Sep 37
3.2.4 | Program signal acquisition using multiplexer | Open | 2018-08-13 | 2018-08-26 | 13 | bar: Sep 37 to Sep 38
3.2.5 | Test signal acquisition by using standard signals | Open | 2018-08-27 | 2018-09-02 | 6 | bar: Sep 39
3.3 | Programming Analog Electronic Configuration | Doing | 2018-09-03 | 2018-12-09 | 97 | bar: Sep 37 to Dec 50
3.3.1 | Set base config. for acquisition of standard signals | Doing | 2018-09-03 | 2018-09-30 | 27 | bar: Sep 37 to Oct 40
3.3.2 | Test base configuration by using standard signals | Open | 2018-10-01 | 2018-10-07 | 6 | bar: Oct 41
3.3.3 | Test base config. with electronic from protoboard | Open | 2018-10-01 | 2018-10-07 | 6 | bar: Oct 41
3.3.4 | Test base config. with PCB analog electronic | Open | 2018-11-26 | 2018-12-09 | 13 | bar: Dec 49 to Dec 50
3.4 | Communication MCU - Mobile | Doing | Doing | 2018-10-07 | #VALUE! | bar: Aug 33 to Oct 41
3.4.1 | Identify and order communication module | Doing | 2018-08-06 | 2018-08-19 | 13 | bar: Aug 33 to Aug 34
3.4.2 | Program communication between MCU & Mobile | Open | 2018-08-13 | 2018-09-02 | 20 | bar: Aug 34 to Sep 36
3.4.3 | Test communication by sending dummy sequences | Open | 2018-09-03 | 2018-09-16 | 13 | bar: Sep 37 to Sep 38
3.4.4 | Test communication by sending known signal | Open | 2018-09-03 | 2018-09-16 | 13 | bar: Sep 37 to Sep 38
3.4.5 | Test communication by sending biosignals | Open | 2018-10-01 | 2018-10-07 | 6 | bar: Oct 41
3.5 | PCB Final Hardware | Open | 2018-09-03 | 2018-12-09 | 97 | bar: Sep 37 to Dec 50
3.5.1 | Select MCU that covers requirements | Open | 2018-09-03 | 2018-09-16 | 13 | bar: Sep 37 to Sep 38
3.5.2 | Design PCB layout with analog electronics | Open | 2018-09-10 | 2018-10-14 | 34 | bar: Sep 38 to Oct 42
3.5.3 | Contact 5 suppliers to manufacture prototype | Open | 2018-09-03 | 2018-09-30 | 27 | bar: Sep 37 to Oct 40
3.5.4 | Receive 3 RFQs | Open | 2018-10-01 | 2018-10-28 | 27 | bar: Oct 41 to Oct 44
3.5.5 | Perform PO | Open | 2018-10-22 | 2018-11-18 | 27 | bar: Oct 44 to Nov 47
3.5.6 | Receive PCB prototype | Open | 2018-11-19 | 2018-11-26 | 7 | bar: Nov 48
3.5.7 | Validate prototype | Open | 2018-11-27 | 2018-12-09 | 12 | bar: Dec 49 to Dec 50
Note on B15: Lopez Arce Vivas, Eduardo: Filters with digital potentiometers should be available in protoboard (2.3.7 done)
Note on B19: Lopez Arce Vivas, Eduardo: PCB must be available (2.5.6 done). Task done in parallel with 2.5.7.
Note on B25: Lopez Arce Vivas, Eduardo: Instrumentation should be at least ready in protoboard (ID 2.4.5 done)
Note on B26: Lopez Arce Vivas, Eduardo: From 3.5.3 to 3.5.7, the same steps are followed as in 2.5.3 to 2.5.7. The ggoal is to order only one PCB
Note on B28: Lopez Arce Vivas, Eduardo: Start designing PCB for digital electronics and then use the task 2.5.2 as base to finishe the final PCB