## Phase 1
ID | Task | Status | Start Date | Due Date | Duration | Y | 2018 | [28 empty] | Open | 96 | 70.07%
[6 empty] | M | Jun |  | Jul |  |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Doing | 22 | 16.06%
[6 empty] | CW | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | Closed | 19 | 13.87%
0. | Project Kick-off | Closed | 2018-06-24 | 2018-06-24 | 0
1. | Project Planning | Doing | 2018-06-24 | 2018-08-12 | 49
1.1 | Project Management | Closed | 2018-06-24 | 2018-08-12 | 49
1.1.1 | Define project management tool 12/08/2018: Github | Closed | 2018-07-28 | 2018-08-05 | 8
1.1.2 | Set project deadlines | Closed | 2018-06-24 | 2018-08-05 | 42
1.1.3 | Describe project tasks | Closed | 2018-06-24 | 2018-07-29 | 35
1.1.4 | Create project timeline in Excel | Closed | 2018-07-23 | 2018-07-29 | 6
1.1.5 | Integrate project tasks in PM tool | Closed | 2018-07-30 | 2018-08-12 | 13
1.1.6 | Create project timeline in PM tool | Closed | 2018-07-30 | 2018-08-19 | 20
1.2 | Finance | Closed | 2018-06-24 | 2018-08-05 | 42
1.2.1 | Agree on available budget for phase 1 | Closed | 2018-06-24 | 2018-06-24 | 0
1.2.2 | Identify options to make money transfer | Closed | 2018-06-30 | 2018-07-15 | 15
1.2.3 | Decide on money transfer method | Closed | 2018-07-15 | 2018-07-15 | 0
1.2.4 | Transfer initial part of budget | Closed | 2018-07-29 | 2018-08-03 | 5
1.2.5 | Create accounting list | Closed | 2018-07-15 | 2018-08-05 | 21
1.3 | State of the Art | Doing | 2018-06-24 | 2018-08-12 | 49
1.3.1 | Identify main competitors | Doing | 2018-06-24 | 2018-08-12 | 49
1.3.2 | Create company profile of main competitors | Doing | 2018-07-29 | 2018-08-12 | 14
1.3.4 | Research on MCUs or platforms for prototyping | Closed | 2018-06-24 | 2018-08-05 | 42
1.4 | Electronic Components | Doing | 2018-07-15 | 2018-08-19 | 35
1.4.1 | Create list of components necessary to start | Doing | 2018-07-15 | 2018-08-05 | 21
1.4.2 | Clarify which components are available at Tec 12/08/2018: Arduino and Bitalino | Closed | 2018-08-06 | 2018-08-12 | 6
1.4.3 | Buy missing components | Doing | 2018-08-13 | 2018-08-19 | 6
1.4.4 | Define tool for electronic design 12/08/2018: Eagle | Closed | 2018-07-30 | 2018-08-12 | 13
2. | Analog Electronics | Doing | 2018-07-30 | 2018-12-09 | 132
2.1 | Preamplification | Doing | 2018-08-06 | 2018-08-19 | 13
2.1.1 | Identify gain ranges for pre-amplification | Doing | 2018-08-06 | 2018-08-19 | 13
2.1.2 | Define instrumental amplifier to be used 12/08/2018: AD620 | Closed | 2018-08-06 | 2018-08-12 | 6
2.1.3 | Calculate needed ranges of digital potentiometers | Doing | 2018-08-06 | 2018-08-19 | 13
2.1.4 | Identify and buy digital potentiomet. and InsAmp. | Doing | 2018-08-06 | 2018-08-19 | 13
2.1.5 | Build preamplification circuit in protoboard | Open | 2018-08-06 | 2018-08-19 | 13
2.1.6 | Test preamplification circuit | Open | 2018-08-13 | 2018-08-19 | 6
2.1.7 | Define final potentiomet. and InsAmp. to be used | Open | 2018-08-13 | 2018-08-19 | 6
2.1.8 | Design preamplification circuit for PCB | Open | 2018-08-13 | 2018-08-19 | 6
2.2 | Multiplexer | Doing | 2018-07-30 | 2018-09-02 | 34
2.2.1 | Research types of analog multiplexers | Doing | 2018-07-30 | 2018-08-19 | 20
2.2.2 | Identify and order 3 analog multiplexers | Open | 2018-08-06 | 2018-08-19 | 13
2.2.3 | Receive multiplexer | Open | 2018-08-13 | 2018-08-26 | 13
2.2.4 | Build multiplexer + preamplification in protoboard | Open | 2018-08-20 | 2018-09-02 | 13
2.2.5 | Test signal quality with multiplexer | Open | 2018-08-27 | 2018-09-02 | 6
2.2.6 | Verify maximum signal frequency with multiplexer | Open | 2018-08-27 | 2018-09-02 | 6
2.2.7 | Define multiplexer to be used | Open | 2018-08-27 | 2018-09-02 | 6
2.2.8 | Design multiplexer circuit for PCB | Open | 2018-08-27 | 2018-09-02 | 6
2.3 | Filters | Doing | 2018-08-13 | 2018-09-09 | 27
2.3.1 | Identify frequency ranges for biosignals | Doing | 2018-08-13 | 2018-08-26 | 13
2.3.2 | Calculate ranges of digital pot. for low-pass filters | Open | 2018-08-13 | 2018-08-26 | 13
2.3.3 | Calculate ranges of digital pot. for high-pass filters | Open | 2018-08-13 | 2018-08-26 | 13
2.3.4 | Design cut-band filter at 60Hz | Open | 2018-08-13 | 2018-08-26 | 13
2.3.5 | Identify and buy digital pot. for all frequency ranges | Open | 2018-08-20 | 2018-09-02 | 13
2.3.6 | Build filter + multiplexer + preamp. in protoboard | Open | 2018-09-03 | 2018-09-09 | 6
2.3.7 | Test filters with different frequency ranges | Open | 2018-09-03 | 2018-09-09 | 6
2.3.8 | Define components for filter circuit | Open | 2018-09-03 | 2018-09-09 | 6
2.3.9 | Design filter circuit for PCB | Open | 2018-09-03 | 2018-08-16 | 0
2.4 | Final Amplification | Open | 2018-09-10 | 2018-09-30 | 20
2.4.1 | Identify gain ranges for final amplification | Open | 2018-09-10 | 2018-09-16 | 6
2.4.2 | Calculate needed ranges of digital potentiometers | Open | 2018-09-10 | 2018-09-16 | 6
2.4.3 | Identify and buy digital potentiometers | Open | 2018-09-10 | 2018-09-23 | 13
2.4.4 | Build amp+filter+multiplexer+preamp in protoboard | Open | 2018-09-24 | 2018-09-30 | 6
2.4.5 | Test amplification circuit | Open | 2018-09-24 | 2018-09-30 | 6
2.4.6 | Define digital potentiometers to be used | Open | 2018-09-24 | 2018-09-30 | 6
2.4.7 | Design amplification circuit for PCB | Open | 2018-09-24 | 2018-09-30 | 6
2.5 | PCB Analog Electronic | Open | 2018-09-03 | 2018-12-09 | 97
2.5.1 | Integrate all phases in PCB design | Open | 2018-09-24 | 2018-10-07 | 13
2.5.2 | Create electronic/PCB layout | Open | 2018-10-01 | 2018-10-07 | 6
2.5.3 | Contact 5 suppliers to manufacture prototype | Open | 2018-09-03 | 2018-09-30 | 27
2.5.4 | Receive 3 RFQs | Open | 2018-10-01 | 2018-10-28 | 27
2.5.5 | Perform PO | Open | 2018-10-22 | 2018-11-18 | 27
2.5.6 | Receive PCB prototype | Open | 2018-11-19 | 2018-11-25 | 6
2.5.7 | Validate prototype | Open | 2018-11-26 | 2018-12-09 | 13
3. | Digital Electronics | Doing | 2018-07-30 | 2018-12-09 | 132
3.1 | Microcontroller Requirements | Doing | 2018-07-30 | 2018-08-19 | 20
3.1.1 | Define inputs needed for signal acquisition | Doing | 2018-08-06 | 2018-08-19 | 13
3.1.2 | Define outputs needed for digital potentiometers | Open | 2018-08-06 | 2018-08-19 | 13
3.1.3 | Decide on communication protocol - MCU & Mobile 12/08/2018: Bluetooth | Closed | 2018-07-30 | 2018-08-12 | 13
3.2 | Programming Signal Acquisition | Open | 2018-08-06 | 2018-09-02 | 27
3.2.1 | Program signal acquisition in MCU | Open | 2018-08-06 | 2018-08-12 | 6
3.2.2 | Design and implement signal validation tool | Open | 2018-08-06 | 2018-08-19 | 13
3.2.3 | Test signal acquisition by using standard signals | Open | 2018-08-13 | 2018-08-19 | 6
3.2.4 | Program signal acquisition using multiplexer | Open | 2018-08-13 | 2018-08-26 | 13
3.2.5 | Test signal acquisition by using standard signals | Open | 2018-08-27 | 2018-09-02 | 6
3.3 | Programming Analog Electronic Configuration | Open | 2018-09-03 | 2018-12-09 | 97
3.3.1 | Set base config. for acquisition of standard signals | Open | 2018-09-03 | 2018-09-30 | 27
3.3.2 | Test base configuration by using standard signals | Open | 2018-10-01 | 2018-10-07 | 6
3.3.3 | Test base config. with electronic from protoboard | Open | 2018-10-01 | 2018-10-07 | 6
3.3.4 | Test base config. with PCB analog electronic | Open | 2018-11-26 | 2018-12-09 | 13
3.4 | Communication MCU - Mobile | Open | 2018-08-06 | 2018-10-07 | 62
3.4.1 | Identify and order communication module | Open | 2018-08-06 | 2018-08-19 | 13
3.4.2 | Program communication between MCU & Mobile | Open | 2018-08-13 | 2018-09-02 | 20
3.4.3 | Test communication by sending dummy sequences | Open | 2018-09-03 | 2018-09-16 | 13
3.4.4 | Test communication by sending known signal | Open | 2018-09-03 | 2018-09-16 | 13
3.4.5 | Test communication by sending biosignals | Open | 2018-10-01 | 2018-10-07 | 6
3.5 | PCB Final Hardware | Open | 2018-09-03 | 2018-12-09 | 97
3.5.1 | Select MCU that covers requirements | Open | 2018-09-03 | 2018-09-16 | 13
3.5.2 | Design PCB layout with analog electronics | Open | 2018-09-10 | 2018-10-14 | 34
3.5.3 | Contact 5 suppliers to manufacture prototype | Open | 2018-09-03 | 2018-09-30 | 27
3.5.4 | Receive 3 RFQs | Open | 2018-10-01 | 2018-10-28 | 27
3.5.5 | Perform PO | Open | 2018-10-22 | 2018-11-18 | 27
3.5.6 | Receive PCB prototype | Open | 2018-11-19 | 2018-11-26 | 7
3.5.7 | Validate prototype | Open | 2018-11-27 | 2018-12-09 | 12
4. | Interface MCU - Mobile | Open | 2018-09-24 | 2018-12-14 | 81
4.1 | Hardware Configuration | Open | 2018-09-24 | 2018-12-09 | 76
4.1.1 | Design and program mobile MCU configuration | Open | 2018-09-24 | 2018-10-14 | 20
4.1.2 | Test config with protoboard and known signals | Open | 2018-10-15 | 2018-10-21 | 6
4.1.3 | Test config with protoboard and biosignals | Open | 2018-10-15 | 2018-10-21 | 6
4.1.4 | Test config with protoboard and biosignals | Open | 2018-11-26 | 2018-12-09 | 13
4.2 | Signal Display in Mobile Device | Open | 2018-09-24 | 2018-10-28 | 34
4.2.1 | Create mobile function that plots acquired signals | Open | 2018-09-24 | 2018-10-14 | 20
4.2.2 | Test function with known signals | Open | 2018-10-08 | 2018-10-21 | 13
4.2.3 | Test function using biosignals | Open | 2018-10-15 | 2018-10-21 | 6
4.2.4 | Integrate function in mobile application | Open | 2018-10-22 | 2018-10-28 | 6
4.3 | App Design | Open | 2018-10-01 | 2018-12-14 | 74
4.3.1 | Optimize design of application | Open | 2018-10-29 | 2018-11-11 | 13
4.3.2 | Contact 5 suppliers to design the application | Open | 2018-10-01 | 2018-10-28 | 27
4.3.3 | Receive 3 RFQs | Open | 2018-10-22 | 2018-11-11 | 20
4.3.4 | Perform PO | Open | 2018-11-12 | 2018-11-18 | 6
4.3.5 | Receive application | Open | 2018-11-19 | 2018-12-14 | 25
4.3.6 | Validate application | Open | 2018-12-08 | 2018-12-14 | 6
5. | Cloud Solution | Doing | 2018-08-06 | 2018-12-14 | 130
5.1 | Communication Mobile - Database | Doing | 2018-08-06 | 2018-10-21 | 76
5.1.1 | Design database layout | Doing | 2018-08-06 | 2018-09-02 | 27
5.1.2 | Create web-based database | Open | 2018-08-20 | 2018-09-16 | 27
5.1.3 | Define and program interface btw mobile and DB | Open | 2018-08-27 | 2018-09-02 | 6
5.1.4 | Test saving dummy sequences from mobile to DB | Open | 2018-09-17 | 2018-09-30 | 13
5.1.5 | Test saving biosignals acquired from hardware | Open | 2018-10-08 | 2018-10-21 | 13
5.2 | Signal Display | Open | 2018-09-17 | 2018-11-11 | 55
5.2.1 | Create function that plots saved signals in the DB | Open | 2018-09-17 | 2018-10-07 | 20
5.2.2 | Test function by plotting known signal | Open | 2018-10-01 | 2018-10-07 | 6
5.2.3 | Create function that plots online signals | Open | 2018-10-08 | 2018-10-28 | 20
5.2.4 | Test function by plotting known signal | Open | 2018-10-22 | 2018-11-04 | 13
5.2.5 | Test function by plotting biosignals | Open | 2018-10-29 | 2018-11-11 | 13
5.3 | Web Design | Open | 2018-10-01 | 2018-12-14 | 74
5.3.1 | Optimize design of application* If not outsourced | Open | 2018-10-29 | 2018-11-11 | 13
5.3.2 | Contact 5 suppliers to design the application | Open | 2018-10-01 | 2018-10-28 | 27
5.3.3 | Receive 3 RFQs | Open | 2018-10-22 | 2018-11-11 | 20
5.3.4 | Perform PO | Open | 2018-11-12 | 2018-11-18 | 6
5.3.5 | Receive application | Open | 2018-11-19 | 2018-12-14 | 25
5.3.6 | Validate application | Open | 2018-12-10 | 2018-12-14 | 4
Note on B88: Lopez Arce Vivas, Eduardo: Filters with digital potentiometers should be available in protoboard (2.3.7 done)
Note on B92: Lopez Arce Vivas, Eduardo: PCB must be available (2.5.6 done). Task done in parallel with 2.5.7.
Note on B98: Lopez Arce Vivas, Eduardo: Instrumentation should be at least ready in protoboard (ID 2.4.5 done)
Note on B99: Lopez Arce Vivas, Eduardo: From 3.5.3 to 3.5.7, the same steps are followed as in 2.5.3 to 2.5.7. The ggoal is to order only one PCB
Note on B101: Lopez Arce Vivas, Eduardo: Start designing PCB for digital electronics and then use the task 2.5.2 as base to finishe the final PCB
Note on B109: Lopez Arce Vivas, Eduardo: Task 3.3 shall be finished before testing this
Note on B113: Lopez Arce Vivas, Eduardo: Part of prototype validation
Note on B117: Lopez Arce Vivas, Eduardo: Instrumentation should be at least ready in protoboard (ID 2.4.5 done) Test of acquiring biosignals with mobile device done (ID 3.4.5 done)
Note on B133: Lopez Arce Vivas, Eduardo: Instrumentation should be at least ready in protoboard (ID 2.4.5 done) Test of acquiring biosignals with mobile device done (ID 3.4.5 done)
Note on B139: Lopez Arce Vivas, Eduardo: Biosignals saved in dabatase must have been tested before (Task 4.1.5 done)

## Tasks Tech
Project Planning | Analog Electronics | Digital Electronics | Interface MCU - Mobile | Cloud solution
Project Management | Preamplification | Microcontroller Selection | Hardware Configuration | Communication Mobile - Database
Define project management tool | Identify gain ranges for pre-amplification | Identify and order development platform for programming (Raspberry Pi, Arduino) | Design and program mobile application that configures the MCU, which then configures the hardware (filters, amplification, etc.). | Design database layout
Set project deadlines | Define instrumental amplifier to be used | Define inputs needed for signal acquisition | Test base configuration with analog electronic protoboard using known signals as input | Create web-based database
Describe project tasks | Calculate needed ranges of digital potentiometers | Define outputs needed for digital potentiometers | Test base configuration with analog electronic protoboard using biosignals as input | Define and program interface between mobile device and database
Create project timeline in Excel | Identify and order digital potentiometers and instrumental amplifier | Decide on communication protocol between microcontroller and mobile device (Bluetooth, Wi-Fi) | Test base configuration with PCB | Test saving dummy sequences sent from mobile to database
Integrate project timeline in project management tool | Build preamplification circuit in protoboard | Select MCU that covers requirements | Signal Display | Test saving biosignals acquired from hardware
Create project timeline in project management tool | Test preamplification circuit | Programming analog electronic configuration | Design and program mobile function that plots acquired signals from the MCU | Signal Display
Finance | Define digital potentiometers and instrumental amplifier to be used | Program signal acquisition of x ports using multiplexer | Test function with known signals | Create function that plots saved signals in the database
Agree on available budget for phase 1 | Design preamplification circuit for PCB | Test signal acquisition by using standard signals; e.g., sine with different frequencies | Test function using biosignals | Test function by plotting known signal
Identify options to make money transfer | Multiplexer | Set base configuration for acquisition of standard signal (EEG, EMG, etc.) | Integrate function in mobile application | Create function that plots online signals acquired from the HW
Decide on money transfer method | Research types of analog multiplexers | Test base configuration by using standard signals | App Design* | Test function by plotting known signal
Transfer initial part of budget | Identify and order 3 analog multiplexers | Test base configuration with analog electronic from protoboard | Optimize design of application* If not outsourced | Test function by plotting biosignals
Create accounting list | Build multiplexer + preamplification circuit in protoboard | Test base configuration with PCB analog electronic | Contact 5 suppliers to design the application | Web Design
Transfer second part of budget | Test signal quality with multiplexer | Communication MCU - Mobile | Receive 3 RFQs | Optimize design of application* If not outsourced
State of the art | Verify maximum signal frequency possible with multiplexer | Identify and order communication module if necessary (e.g., Bluetooth or Wi-Fi) | Perform PO | Contact 5 suppliers to design the application
Identify main competitors | Define multiplexer to be used | Program communication between microcontroller and mobile | Receive application | Receive 3 RFQs
Create company profile of main competitors | Design multiplexer circuit for PCB | Test communication by sending dummy sequences (e.g., 1 to 100) | Validate application | Perform PO
Investigate characteristics of analog multiplexers | Filters | Test communication by sending known signal (e.g., sine with different frequencies) |  | Receive application
Research on MCUs or platforms available for prototyping (e.g., Arduino, Raspberry Pi) | Identify frequency ranges for biosignals | Test communication by sending biosignals |  | Validate application
Electronic Components | Calculate ranges of digital potentiometers for low-pass filters | PCB Final Hardware
Create list of components necessary to start the project | Calculate ranges of digital potentiometers for high-pass filters | Design PCB layout with analog electronics
Clarify which components are available at Tec | Design cut-band filter at 60Hz | Contact 5 suppliers to manufacture prototype
Perform PO for missing components | Identify and order digital potentiometers for all frequency ranges | Receive 3 RFQs
| Build filter circuit + multiplexer + preamplification in protoboard | Perform PO
| Test filters with different frequency ranges | Receive PCB prototype
| Define components for filter circuit (OpAmp, potentiometers and capacitors) | Validate prototype
Design filter circuit for PCB
Final amplification
Identify gain ranges for final amplification
Calculate needed ranges of digital potentiometers
Identify and order digital potentiometers
Build amplification circuit + filter circuit + multiplexer + preamplification in protoboard
Test amplification circuit
Define digital potentiometers to be used
Design amplification circuit for PCB
PCB analog electronic
Integrate all phases in PCB design
Create PCB layout
Contact 5 suppliers to manufacture prototype
Receive 3 RFQs
Perform PO
Receive PCB prototype
Validate prototype

## Tasks Mgt
Business Plan | Company | Funding | Operations | Intellectual Property
Company Profile | Foundation | Horizon 2020 | Import/Export | General Information
Create company's description | Investigate requirements for UG and GmbH foundation
Generate profile of company's members | Investigate requirements for S.A. de C.V. foundation |  |  | International Patent
Describe products and services | Investigate collaboration or synergy between S.A. de C.V. and UG/GmbH | Funding Programs: EU
Market Research | Found UG or GmbH
Evaluate market size and expected growth for electronic medical devices | Found S.A. de C.V. (if needed)
Evaluate market size and expected growth for eHealth | Tax Consulting | Funding Programs: Germany |  | European Patent
Evaluate market size and expected growth for development microcontroller platforms | Receive 3 RFQs from tax consultants in Germany
Analyze main competitors | Hire tax consultant in Germany
Strategy and Implementation | Receive 3 RFQs from tax consultants in Mexico (if needed) | Funding Programs: Mexico |  | US Patent
Define marketing plan to promote the business and enter the market | Hire tax consultant in Mexico (if needed)
Evaluate impact of Hackathon with prototype | Accounting Tool
Make feasibility analysis for crowdfunding campaign | Investigate accounting tools | Funding Programs: Jalisco
Describe pricing, promotion, distribution and logistics | Define accounting tool to be used
Financial Analysis | HR Tool
Create historical financial data: income statements, balance sheets and cash flow statements | Define tool to be used for company's email (e.g., tool to connect external email to email account) | Crowdfunding
Estimate financial situation for the company's first 5 years | Website
Receive 3 RFQs to outsource website
Outsource website design (Front End)
Generate initial emails with company's website
Integrate Web Solution to company's website (Front End)