## Sheet1
ID | Task | Aug | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec
4 | Application Design (Interface & Cloud) | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53
4.1 | Design Application Layout
4.1.1 | Create interface for display data | bar: Aug 35
4.1.1.1 | Main Menu Layout | bar: Aug 35
4.1.1.2 | Authentification Layout | bar: Aug 35
4.1.1.3 | Biosignal Display Layout | bar: Aug 35
4.1.1.4 | MCU Display Layout | bar: Aug 35
4.1.1.5 | Patient/User Info Display Layout | bar: Aug 35
4.1.1.6 | Storage/Cloud Access Display Layout | bar: Aug 35
4.2 | Software Configuration
4.2.1 | Choose programming language | bar: Aug 35
4.2.2 | Data Display Code | bar: Sep 36 to Nov 47
4.2.3 | Main Menu Code | bar: Sep 36 to Nov 47
4.2.4 | Authentification Code | bar: Sep 36 to Nov 47
4.2.5 | Biosignal Display Code | bar: Sep 36 to Nov 47
4.2.6 | MCU Display Code | bar: Sep 36 to Nov 47
4.2.7 | Patien/User Info Display Code | bar: Sep 36 to Nov 47
4.2.8 | Storage/Cloud Access Display Code | bar: Sep 36 to Nov 47
4.3 | Hardware Configuration | bar: Oct 40 to Nov 47
4.3.1 | Test Bluetooth connection (Send) | bar: Oct 40 to Nov 47
4.3.2 | Test Bluetooth connection (Receive) | bar: Oct 40 to Nov 47
4.3.3 | Test config with protoboard and known signals | bar: Oct 40 to Nov 47
4.3.4 | Test config with protoboard and biosignals | bar: Oct 40 to Nov 47
4.4 | Signal Processing | bar: Oct 40 to Dec 49
4.4.1 | Amplifications | bar: Oct 40 to Dec 49
4.4.2 | Filters | bar: Oct 40 to Dec 49
4.4.3 | Signal Conditioning (Rect, Prom, Offset, etc) | bar: Oct 40 to Dec 49
4.5 | Outsource App and Web design
4.5.1 | Optimize application design | bar: Dec 49 to Dec 53
4.5.2 | Contact 5 suppliers to design the application | bar: Dec 49 to Dec 53
4.5.3 | Receive 3 RFQs | bar: Dec 49 to Dec 53
4.5.4 | Perform PO | bar: Dec 49 to Dec 53
4.5.5 | Receive application | bar: Dec 49 to Dec 53
4.5.6 | Validate application | bar: Dec 49 to Dec 53